## Plan
Project Name: | Reascent | Start Time: | 20110510 | Resource: | Sun Jian | Environment: | Win NT
Full Name: | Reascent framework | estimate Time: | 20120510 |  | Liu Haifei
Project goal: | Simple premise is stable
[5 empty] | schedule |  | Actual
Task NO | Task description | Main Job | Status | RRESonsible | Start date | End date | begain date | over date | QA person | QA result | Note | 流程处理图 | 列3 | 列4
Phase 1--design
RES10000 | Install JDK5.0, eclipse 3.4 IDE and my eclipse 7.0 plugin | 安装开发环境 |  | brain storm
RES10001 | Install application server Jboss 6.0 | 搭建应用服务器 |  | brain storm
RES10002 | Install DB server oracle and client, test connection | 安装数据库服务器和客户端 |  | brain storm
RES10003 | Build google code | 搭建google code 版本控制 |  | brain storm
RES10004 | Decide spring struts version | 确定spring struts版本以及第三方jar包 |  | brain storm
RES10005 | Code format style | 确定code format style |  | brain storm
RES10006 | Build workspace | 搭建工作空间,项目结构设计 |  | brain storm
RES10007 | Design JAAS security | JAAS 设计 |  | brain storm
RES10008 | Design the domain model and data model | 设计领域模型，数据模型 |  | brain storm
RES10009 | Merge the spring and struts framework | 整合spring和struts框架 |  | brain storm
RES10010 | Design the struts validation and actionform config | 设计struts校验规则和动态frombean的配置规则 |  | brain storm
RES10011 | Transaction control solution | 事务控制方案 |  | brain storm
RES10012 | Make solution for Exception handle | 异常定制,统一处理 |  | brain storm
RES10013 | Constant variable cache object and system proerty structure | 构造常量,系统属性 |  | brain storm
RES10014 | Resource and message | 国际化消息处理 |  | brain storm
RES10015 | System logging（i/o,systemout） | 系统日志处理 |  | brain storm
RES10016 | Design and implement the base action interface , functions | Base action 的设计与实现 |  | brain storm
RES10017 | Create test demo and build test project workspace | 测试工程创建和测试列子实现 |  | brain storm
Phase 2--framework implementation
RES10018 | JNDI database source config | 数据源可配置，低耦合
RES10019 | Implements DB connect factory module | 实现数据库连接，关闭公用模块
RES10020 | Implements transaction control | 事务控制方案实现
RES10021 | implements config management | 实现配置文件统一管理
RES10022 | implements session management | 实现session统一管理
RES10023 | implements application user management | 实现应用用户管理
RES10024 | Implements Login management | 实现登录模块化，统一管理
RES10025 | Implements JAAS Login module | 提取JAAS为登录模块
RES10026 | Implements check session invalid module | 实现sessionScaner ，动态扫描过期或者清理无效session
RES10027 | Design main page | 设计主界面（静态）
RES10028 | Design menu page | 设计菜单页（静态）
RES10029 | Design head and home pages | 设计页面和home页面（静态）
RES10030 | Implements home and menu pages | 实现页面和home页面动态可配置化
RES10031 | Unit Test | Unit Test
RES10032 | System internal test | System internal test
Phase 3--develop ESP application
RES10033 | Create domain objects | 创建领域模型对象
RES10034 | Create DB tables,and alog tables,export ddl and ERD | 创建数据库表,备份table,DDL,导出ER图
RES10035 | Define base DAO interface use the spring DAO template | 定义DAO接口，利用spring DAO模板实现base DAO
RES10036 | Implement User manangement(C R U D) , login module | 实现用户管理，登陆
RES10037 | Implement user information management(C R U D) | 实现用户详细信息管理
RES10038 | Implement user password history manangement | 实现用户密码修改，备份记录
RES10039 | Implement Role management(C R U D) | 实现角色管理
RES10040 | Implement user Role assignment | 实现用户与角色的指派
RES10041 | Implement application management(C R U D) | 实现应用管理
RES10042 | Implement menu management(C R U D)(menu,menu folder,separetor) | 实现菜单管理
RES10043 | Implement Role menu assignment | 实现角色，菜单指派
RES10044 | Implement menu page according to system property | 动态构建菜单页（left,drop-down list）
RES10045 | Implement group management(C R U D) | 实现群组管理
RES10046 | Implement user group assignment | 实现用户与群组的指派
RES10047 | Implement group role assignment | 实现角色与群组的指派
RES10048 | Implement resource management(C R U D) | 实现资源模块管理
RES10049 | Implement resource check in action ,display the module or not in pages | 实现资源在页面的使用
RES10050 | Implement DataFilterItem management(C R U D) | 实现数据过滤元素管理
RES10051 | Implement DataFilter management(C R U D) | 实现数据过滤器管理
RES10052 | Implement group datafilter assignment | 实现群组过滤器指派
RES10053 | Implement user datafilter assignment | 实现用户过滤器指派
RES10054 | Implement data filter in bussiness | 实现数据过滤业务
RES10055 | Unit Test
RES10056 | System internal test
Phase 4--enhancement:develop the independent moules
RES10057 | Workflow module design | 工作流设计
RES10058 | Set up envonriment for workflow module | 工作流环境搭建
RES10059 | Implement the workflow | 工作流实现
RES10060 | Test workflow | 工作流测试
RES10061 | workflow visualization design | 工作流可视化设计
RES10062 | implement workflow visualization | 工作流可视化实现
RES10063 | Unit Test
RES10064 | System internal test
RES10065 | Smart module design | 快速开发模块设计
RES10066 | Smart module main page design | 快速开发模块主页面设计
RES10067 | Smart module depagination design | 快速开发模块分页设计
RES10068 | Implement smart module main page | 快速开发模块主页面实现
RES10069 | Implement smart module depagination | 快速开发模块分页实现
RES10070 | Smart module can configurationable design | 快速开发模块可配置化设计
RES10071 | Implement smart module can configurationable | 快速开发模块可配置化实现
RES10072 | Smart module visualization design | 快速开发模块可视化设计
RES10073 | Implement smart module visualization | 快速开发模块可视化化实现
RES10074 | Unit Test
RES10075 | System internal test
RES10076 | Document mananment module design | 文档管理模块设计
RES10077 | Document information management | 文档信息管理
RES10078 | Document mananment module design | 文档管理模块设计
RES10079 | Routing the document to special customer or user | 文档路由
RES10080 | Bath upload and download | 批量上传下载
RES10081 | Document console implement(FTP,convert,populate information) | 文档传输，转换格式，信息登记
RES10082 | Unit Test
RES10083 | System internal test
RES10084 | Task schedule module design | 任务调度模块设计
RES10085 | Implement schedule module | 任务调度模块实现

## Design
一.domain
二.Data model
三.主界面
四.系统架构
五.系统层次结构
六.系统实现详图
View
Action
Delegation
Business
DAO Factory/DAO model
DAO
DB
browser
View
html
UI(Jquery)
jsp
Action
BaseAction
Exception
logging
message resource
datafilter
preAction
postAction
doAction
application Action
Delegation Factory
Delegation
Business Interface
Business Interface
Delegation
Business interface
Business
Transaction
implements
DAO Factory
DAO interface
DAO
DAO
DAO interface
config project
base application config
module2 config...
module1 config
User
UserInfo
Function
Application
Resource
Menu
MenuAction
MenuFolder
Role
Group
DataFilter
DataFilterItem
PasswordHistory
??????
?????
Customer
Application Server
Session manager
user manager
init
destory
Session
map
Session Scaner
add session
isAvalid session
active session
remove session
timeout
start
delete
LoginManager
JAAS
Login
new
Logout
Re login
Intercepter
*.do
*.do/login.do
structs-module2.xml
application-module2.xml

## libaray
NO | Name | version | author | remark
1 | struts-2.1.6-all | 2.1.6 | Liu Haifei | struts-2.1.6-all.zip, include all jars which application needs.

## software
NO | Software Name | version | Note | Remark
1 | JDK | 1.6.0 |  | both install jre 1.6.0
2 | Myeclipse | 7.0 or 7.5
3 | Jboss | 6 | Final release version